## Defects
Root Cause Analysis (RCA): A column to categorize why the bug occurred (e.g., "Human Error," "API Limitation," or "Integration Issue"). | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rahul vakiti | 2025-12-28 | Unused imports were not being detected correctly for certain Python files | Sprint 1 | Self | Logical | Improved AST traversal logic to correctly identify unused imports | 2025-12-28 | Closed | Issue resolved and validated with sample programs
2 | Rahul vakiti | 2025-12-29 | PEP8 style violations were not highlighted consistently in the output | Sprint 1 | Self | Standards | Root Cause Analysis (RCA): A column to categorize why the bug occurred (e.g., "Human Error," "API Limitation," or "Integration Issue"). | 2025-12-29 | Closed | Style detection accuracy improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others